## Overview
Milestone 3 (Final) | Priority
Networking between players | Abandoned
Handle death and respawn | Top
Implement longsword | Abandoned
Trackers for player performance | Low
Weapon pickup | Abandoned
EventHandler for Slayer game mode | Top
Update frame calculations to time | Top
Shield behavior (visual hit response) | Top
Finish weapon behaviors | Top
Unity visual bug fixes | Low
Melee attack | Medium
Implement player heads | Abandoned
Enemy AI | Top
Entry menu with basic option(s) | Top
(As of beginning Milestone 3)

## Task List
Task | State | Priority | Completed On… | Notes
Identify all perma-deleted scripts | Finished | Bottleneck | 2020-12-15 | FPSInput, gravLift, RayShooter, InitSpawner, LiftGuide, MicroRocket, RocketBoom
Recreate the LARGE missing scripts | Finished | Bottleneck | 2020-12-14 | RayShooter, PlayerInput scripts
LARGE recreate- FPSInput | Finished | Bottle -1 | 2020-12-14 | Restored by implementing Milestone 2 submission of FPSInput
LARGE recreate- RayShooter | Finished | Bottle -1 | 2020-12-14 | Restored by implementing Milestone 2 submission and WanderingAI's mimicry, and adding missing code
Recreate the SMALL missing scripts |  | Bottleneck |  | GravLift, InitSpawner, LiftGuide, MicroRocket, RocketBoom scripts
SMALL recreate- GravLift | Finished | Bottle -1 | 2020-12-14 | Restored by implementing Milestone 2 submission and adding missing code
SMALL recreate- MicroRocket | Finished | Bottle -1 | 2020-12-14 | Restored by implementing code sent to professor for analysis
MicroRocket- rockets don't explode on hit with a player when close | Finished | Bottle -2 | 2020-12-14 | Incorrect logic caused this. This also now allows rocket to pass through user, hooray!!
SMALL recreate- RocketBoom | Finished | Bottle -1 | 2020-12-14 | Restored by implementing Milestone 2 submission and adding missing code
SMALL recreate- InitSpawner | Finished | Bottle -1 | 2020-12-14 | Restored by remembering the code
SMALL recreate- LiftGuide | Finished | Bottle -1 | 2020-12-14 | Restored by remembering the code
Player Melee attack | Abandoned | Medium
Player HUD | Finished | Top | 2020-12-17
Shields and Health | Finished | Top -1 | 2020-12-17
Event Announcer | Finished | Top -1 | 2020-12-17
Scores | Finished | Top -1 | 2020-12-17
Movement tracker and "advanced" HUD | Abandoned | Low
Fake weapon (pointer) points at aim spot | Abandoned | Low
Networking between players | Abandoned | Top | N/A | After much trial and tribulation, the professor advised me to abandon this and trade for AI
Reverse changes for networking support | Finished | Bottleneck | 12/8/20? | This broke a lot of things, actually. It was a full day endeavor to undo it all properly.
Basic AI- Movement | Finished | Top | 2020-12-10
Basic AI- Use gravity lifts properly | Finished | Bottleneck | 2020-12-12 | Created "LiftBoxes" near gravity lifts that tell AI to prioritize using the gravity lift if near one
Basic AI- Shoot on sight | Finished | Top | 2020-12-15 | Fires straight ahead and not up or down
Shoot with Burst Rifle | Finished | Top -1 | 2020-12-15
Basic AI- mount BR on "eye camera" | Finished | Top -2 | 2020-12-15 | Removed a line of code copied from player version, stopped it from firing at weird angles instead
Shoot with Battle Rifle- aim vertically | Finished | Top -2 | 2020-12-15 | Result of 'Basic AI- mount BR on "eye camera"', accidental success!
Shoot with Micro-Rockets | Finished | Top -1 | 2020-12-16
Shoot with Micro-Rockets- don't bounce off self | Finished | Top -2 | 2020-12-16 | Removed capsule colliders for all players. This also fixed the double-hit explosion bug!
Basic AI- Look at attacker when hit | Abandoned | Medium
Basic AI- Create AI "herders" for slope corners | Finished | Top | 2020-12-15 | Dubbed "AI Walls"
Advanced AI- melee attack | Abandoned | Low | N/A
Advanced AI- weapon preferences | Finished | Medium | 2020-12-13 | Randomly selected when AI spawns or respawns
Advanced AI- jump off edges |  | Low |  | Bumped from Medium to Low priority given time
Convert frame-based calcs to time | Finished | Top | 12/6/20?
Initial spawning | Finished | Top | 2020-12-11
Respawning AI | Finished | Top | 2020-12-11
Handle player death and respawning | Finished | Top | 2020-12-17
Death screen for player | Finished | Top -1 | 2020-12-17
Respawn player | Finished | Top -1 | 2020-12-17
Smarter spawning to prevent spawn-ons | Abandoned | Low | N/A
Prevent players respawning at the same spot | Finished | Medium | 2020-12-12
Trackers for player performance | Finished | Low | 2020-12-17 | Accidentally completed as a result of score tracking
Assist kill tracker | Abandoned | Low -1 | N/A
Weapon pickups | Abandoned | Top | N/A
Two-weapon carry limit | Abandoned | Medium | N/A
EventHandler for Slayer game mode | Finished | Top | 2020-12-17
Handle starting game | Finished | Top -1 | 2020-12-17
Handle ending game | Finished | Top -1 | 2020-12-17
Unity lighting bug fixes | Abandoned | Lowest | N/A
Player heads / Burst Rifle headshots | Abandoned | Low | N/A | Burst Rifle is already kinda insane, I don't think it needs headshots
Weapon ammo and reloading | Abandoned | Medium | N/A
Weapon reloading | Abandoned | Medium | N/A
Main Menu with basic option(s) |  | Top
Camera rotating around map in main menu | Abandoned | Low | N/A